## WP1-Prg
Date: | 2022-05-04 |  | Issue | 1
Project | LhARA | Laser-hybrid Accelerator for Radiobiological Applications
Work package | WP1 | LhARA Project Management
Manager | WPMs | Colin Whyte & Jason Parsons
Header | Task | Month | Date | Planned fraction complete | Planned value (£k) | Fraction complete | Spend (£k)
ProgressLine | Project office support | 1 | 2022-11-01 | 0.041667 | 8
ProgressLine | Project office support | 2 | 2023-01-01 | 0.083333 | 16
ProgressLine | Project office support | 3 | 2023-02-01 | 0.125 | 24
ProgressLine | Project office support | 4 | 2023-03-01 | 0.16667 | 32
ProgressLine | Project office support | 5 | 2023-04-01 | 0.20833 | 40
ProgressLine | Project office support | 6 | 2023-05-01 | 0.25 | 48
ProgressLine | Project office support | 7 | 2023-06-01 | 0.29167 | 56
ProgressLine | Project office support | 8 | 2023-07-01 | 0.33333 | 64
ProgressLine | Project office support | 9 | 2023-08-01 | 0.375 | 72
ProgressLine | Project office support | 10 | 2023-09-01 | 0.41667 | 80
ProgressLine | Project office support | 11 | 2023-10-01 | 0.45833 | 88
ProgressLine | Project office support | 12 | 2023-11-01 | 0.5 | 96
ProgressLine | Project office support | 13 | 2023-12-01 | 0.54167 | 104
ProgressLine | Project office support | 14 | 2024-01-01 | 0.58333 | 112
ProgressLine | Project office support | 15 | 2024-02-01 | 0.625 | 120
ProgressLine | Project office support | 16 | 2024-03-01 | 0.66667 | 128
ProgressLine | Project office support | 17 | 2024-04-01 | 0.70833 | 136
ProgressLine | Project office support | 18 | 2024-05-01 | 0.75 | 144
ProgressLine | Project office support | 19 | 2024-06-01 | 0.79167 | 152
ProgressLine | Project office support | 20 | 2024-07-01 | 0.83333 | 160
ProgressLine | Project office support | 21 | 2024-08-01 | 0.875 | 168
ProgressLine | Project office support | 22 | 2024-09-01 | 0.91667 | 176
ProgressLine | Project office support | 23 | 2024-10-01 | 0.95833 | 184
ProgressLine | Project office support | 24 | 2024-11-01 | 1 | 192
Update history
2022-06-21 | First version
Formulas:
Date = EDATE(D7,[LhARA Project Management])