## WP1-Prg
Date: | 2022-05-04 |  | Issue | 1
Project | LhARA | Laser-hybrid Accelerator for Radiobiological Applications
Work package | WP1 | LhARA Project Management
Manager | WPMs | Colin Whyte & Jason Parsons
Header | Task | Month | Date | Planned fraction complete | Planned value (£k) | Fraction complete | Spend (£k)
ProgressLine | Project office support | 1 | 2022-12-01 | 0.016667 | 26.8375 | 0.0098087 | 15.7945
ProgressLine | Project office support | 2 | 2023-02-01 | 0.033333 | 53.675 | -0.013074 | -21.0531
ProgressLine | Project office support | 3 | 2023-03-01 | 0.05 | 80.5125 | 0.04045 | 65.1343
ProgressLine | Project office support | 4 | 2023-04-01 | 0.066667 | 107.35 | 0.077987 | 125.5786
ProgressLine | Project office support | 5 | 2023-05-01 | 0.083333 | 134.1875 | 0.15284 | 246.1088
ProgressLine | Project office support | 6 | 2023-06-01 | 0.1 | 161.025 | 0.14024 | 225.8237
ProgressLine | Project office support | 7 | 2023-07-01 | 0.11667 | 187.8625 | 0.079256 | 127.6227
ProgressLine | Project office support | 8 | 2023-08-01 | 0.13333 | 214.7 | 0.15376 | 247.5924
ProgressLine | Project office support | 9 | 2023-09-01 | 0.15 | 241.5375 | 0.22357 | 360.0109
ProgressLine | Project office support | 10 | 2023-10-01 | 0.16667 | 268.375 | 0.12738 | 205.1212
ProgressLine | Project office support | 11 | 2023-11-01 | 0.18333 | 295.2125 | 0.16672 | 268.4584
ProgressLine | Project office support | 12 | 2023-12-01 | 0.2 | 322.05 | 0.23832 | 383.7578
ProgressLine | Project office support | 13 | 2024-01-01 | 0.21667 | 348.8875 | 0.20689 | 333.1429
ProgressLine | Project office support | 14 | 2024-02-01 | 0.23333 | 375.725 | 0.23911 | 385.0334
ProgressLine | Project office support | 15 | 2024-03-01 | 0.25 | 402.5625 | 0.2638 | 424.7809
ProgressLine | Project office support | 16 | 2024-04-01 | 0.26667 | 429.4 | 0.22944 | 369.4597
ProgressLine | Project office support | 17 | 2024-05-01 | 0.28333 | 456.2375 | 0.22956 | 369.6562
ProgressLine | Project office support | 18 | 2024-06-01 | 0.3 | 483.075 | 0.35328 | 568.8689
ProgressLine | Project office support | 19 | 2024-07-01 | 0.31667 | 509.9125 | 0.2929 | 471.6459
ProgressLine | Project office support | 20 | 2024-08-01 | 0.33333 | 536.75 | 0.37941 | 610.9511
ProgressLine | Project office support | 21 | 2024-09-01 | 0.35 | 563.5875 | 0.36972 | 595.3417
ProgressLine | Project office support | 22 | 2024-10-01 | 0.36667 | 590.425 | 0.38804 | 624.8376
ProgressLine | Project office support | 23 | 2024-11-01 | 0.38333 | 617.2625 | 0.40849 | 657.7763
ProgressLine | Project office support | 24 | 2024-12-01 | 0.4 | 644.1 | 0.43675 | 703.2713
ProgressLine | Project office support | 25 | 2025-01-01 | 0.41667 | 670.9375 | 0.42488 | 684.1675
ProgressLine | Project office support | 26 | 2025-02-01 | 0.43333 | 697.775 | 0.47982 | 772.6321
ProgressLine | Project office support | 27 | 2025-03-01 | 0.45 | 724.6125 | 0.43229 | 696.0887
ProgressLine | Project office support | 28 | 2025-04-01 | 0.46667 | 751.45 | 0.47626 | 766.9046
ProgressLine | Project office support | 29 | 2025-05-01 | 0.48333 | 778.2875 | 0.43589 | 701.8842
ProgressLine | Project office support | 30 | 2025-06-01 | 0.5 | 805.125 | 0.5435 | 875.174
ProgressLine | Project office support | 31 | 2025-07-01 | 0.51667 | 831.9625 | 0.47484 | 764.6065
ProgressLine | Project office support | 32 | 2025-08-01 | 0.53333 | 858.8 | 0.48921 | 787.7454
ProgressLine | Project office support | 33 | 2025-09-01 | 0.55 | 885.6375 | 0.4863 | 783.0624
ProgressLine | Project office support | 34 | 2025-10-01 | 0.56667 | 912.475 | 0.55651 | 896.1134
ProgressLine | Project office support | 35 | 2025-11-01 | 0.58333 | 939.3125 | 0.56776 | 914.2418
ProgressLine | Project office support | 36 | 2025-12-01 | 0.6 | 966.15 | 0.6063 | 976.3026
ProgressLine | Project office support | 37 | 2026-01-01 | 0.61667 | 992.9875 | 0.59287 | 954.6701
ProgressLine | Project office support | 38 | 2026-02-01 | 0.63333 | 1019.825 | 0.66185 | 1065.7461
ProgressLine | Project office support | 39 | 2026-03-01 | 0.65 | 1046.6625 | 0.63232 | 1018.1893
ProgressLine | Project office support | 40 | 2026-04-01 | 0.66667 | 1073.5 | 0.70656 | 1137.7424
ProgressLine | Project office support | 41 | 2026-05-01 | 0.68333 | 1100.3375 | 0.71002 | 1143.3128
ProgressLine | Project office support | 42 | 2026-06-01 | 0.7 | 1127.175 | 0.71031 | 1143.7837
ProgressLine | Project office support | 43 | 2026-07-01 | 0.71667 | 1154.0125 | 0.71878 | 1157.4179
ProgressLine | Project office support | 44 | 2026-08-01 | 0.73333 | 1180.85 | 0.7024 | 1131.0345
ProgressLine | Project office support | 45 | 2026-09-01 | 0.75 | 1207.6875 | 0.71509 | 1151.4806
ProgressLine | Project office support | 46 | 2026-10-01 | 0.76667 | 1234.525 | 0.83092 | 1337.9867
ProgressLine | Project office support | 47 | 2026-11-01 | 0.78333 | 1261.3625 | 0.74681 | 1202.5509
ProgressLine | Project office support | 48 | 2026-12-01 | 0.8 | 1288.2 | 0.80756 | 1300.3735
ProgressLine | Project office support | 49 | 2027-01-01 | 0.81667 | 1315.0375 | 0.81889 | 1318.6187
ProgressLine | Project office support | 50 | 2027-02-01 | 0.83333 | 1341.875 | 0.85318 | 1373.8308
ProgressLine | Project office support | 51 | 2027-03-01 | 0.85 | 1368.7125 | 0.85822 | 1381.9493
ProgressLine | Project office support | 52 | 2027-04-01 | 0.86667 | 1395.55 | 0.89143 | 1435.4229
ProgressLine | Project office support | 53 | 2027-05-01 | 0.88333 | 1422.3875 | 0.91366 | 1471.2259
ProgressLine | Project office support | 54 | 2027-06-01 | 0.9 | 1449.225 | 0.93337 | 1502.9652
ProgressLine | Project office support | 55 | 2027-07-01 | 0.91667 | 1476.0625 | 0.96153 | 1548.3018
ProgressLine | Project office support | 56 | 2027-08-01 | 0.93333 | 1502.9 | 0.97938 | 1577.045
ProgressLine | Project office support | 57 | 2027-09-01 | 0.95 | 1529.7375 | 0.98904 | 1592.6074
ProgressLine | Project office support | 58 | 2027-10-01 | 0.96667 | 1556.575 | 0.94781 | 1526.2174
ProgressLine | Project office support | 59 | 2027-11-01 | 0.98333 | 1583.4125 | 0.96485 | 1553.6466
ProgressLine | Project office support | 60 | 2027-12-01 | 1 | 1610.25 | 1.0734 | 1728.4972
Update history
2022-06-21 | First version
Formulas:
Date = EDATE(D7,[LhARA Project Management])