## Sheet1
Date: | 2022-05-04 |  | Issue | 1
Project | LhARA | Laser-hybrid Accelerator for Radiobiological Applications
Work package | WP1 | LhARA Project Management
Manager | WPMs | Colin Whyte & Jason Parsons
Header | Task | Month | Date | Planned % complete | % complete | Spend
ProgressLine | Project office support | 1 | 2022-12-01 | 1.667%
ProgressLine | Project office support | 2 | 2023-02-01 | 3.333%
ProgressLine | Project office support | 3 | 2023-03-01 | 5%
ProgressLine | Project office support | 4 | 2023-04-01 | 6.667%
ProgressLine | Project office support | 5 | 2023-05-01 | 8.333%
ProgressLine | Project office support | 6 | 2023-06-01 | 10%
ProgressLine | Project office support | 7 | 2023-07-01 | 11.67%
ProgressLine | Project office support | 8 | 2023-08-01 | 13.33%
ProgressLine | Project office support | 9 | 2023-09-01 | 15%
ProgressLine | Project office support | 10 | 2023-10-01 | 16.67%
ProgressLine | Project office support | 11 | 2023-11-01 | 18.33%
ProgressLine | Project office support | 12 | 2023-12-01 | 20%
ProgressLine | Project office support | 13 | 2024-01-01 | 21.67%
ProgressLine | Project office support | 14 | 2024-02-01 | 23.33%
ProgressLine | Project office support | 15 | 2024-03-01 | 25%
ProgressLine | Project office support | 16 | 2024-04-01 | 26.67%
ProgressLine | Project office support | 17 | 2024-05-01 | 28.33%
ProgressLine | Project office support | 18 | 2024-06-01 | 30%
ProgressLine | Project office support | 19 | 2024-07-01 | 31.67%
ProgressLine | Project office support | 20 | 2024-08-01 | 33.33%
ProgressLine | Project office support | 21 | 2024-09-01 | 35%
ProgressLine | Project office support | 22 | 2024-10-01 | 36.67%
ProgressLine | Project office support | 23 | 2024-11-01 | 38.33%
ProgressLine | Project office support | 24 | 2024-12-01 | 40%
ProgressLine | Project office support | 25 | 2025-01-01 | 41.67%
ProgressLine | Project office support | 26 | 2025-02-01 | 43.33%
ProgressLine | Project office support | 27 | 2025-03-01 | 45%
ProgressLine | Project office support | 28 | 2025-04-01 | 46.67%
ProgressLine | Project office support | 29 | 2025-05-01 | 48.33%
ProgressLine | Project office support | 30 | 2025-06-01 | 50%
ProgressLine | Project office support | 31 | 2025-07-01 | 51.67%
ProgressLine | Project office support | 32 | 2025-08-01 | 53.33%
ProgressLine | Project office support | 33 | 2025-09-01 | 55%
ProgressLine | Project office support | 34 | 2025-10-01 | 56.67%
ProgressLine | Project office support | 35 | 2025-11-01 | 58.33%
ProgressLine | Project office support | 36 | 2025-12-01 | 60%
ProgressLine | Project office support | 37 | 2026-01-01 | 61.67%
ProgressLine | Project office support | 38 | 2026-02-01 | 63.33%
ProgressLine | Project office support | 39 | 2026-03-01 | 65%
ProgressLine | Project office support | 40 | 2026-04-01 | 66.67%
ProgressLine | Project office support | 41 | 2026-05-01 | 68.33%
ProgressLine | Project office support | 42 | 2026-06-01 | 70%
ProgressLine | Project office support | 43 | 2026-07-01 | 71.67%
ProgressLine | Project office support | 44 | 2026-08-01 | 73.33%
ProgressLine | Project office support | 45 | 2026-09-01 | 75%
ProgressLine | Project office support | 46 | 2026-10-01 | 76.67%
ProgressLine | Project office support | 47 | 2026-11-01 | 78.33%
ProgressLine | Project office support | 48 | 2026-12-01 | 80%
ProgressLine | Project office support | 49 | 2027-01-01 | 81.67%
ProgressLine | Project office support | 50 | 2027-02-01 | 83.33%
ProgressLine | Project office support | 51 | 2027-03-01 | 85%
ProgressLine | Project office support | 52 | 2027-04-01 | 86.67%
ProgressLine | Project office support | 53 | 2027-05-01 | 88.33%
ProgressLine | Project office support | 54 | 2027-06-01 | 90%
ProgressLine | Project office support | 55 | 2027-07-01 | 91.67%
ProgressLine | Project office support | 56 | 2027-08-01 | 93.33%
ProgressLine | Project office support | 57 | 2027-09-01 | 95%
ProgressLine | Project office support | 58 | 2027-10-01 | 96.67%
ProgressLine | Project office support | 59 | 2027-11-01 | 98.33%
EndProgressRpt | Project office support | 60 | 2027-12-01 | 100%
Update history
2022-06-21 | First version
Formulas:
Date = EDATE(D7,[LhARA Project Management])