## WP1-Prg
Date: | 2022-05-04 |  | Issue | 1
Project | LhARA | Laser-hybrid Accelerator for Radiobiological Applications
Work package | WP1 | LhARA Project Management
Manager | WPMs | Colin Whyte & Jason Parsons
Header | Task | Month | Date | Planned fraction complete | Fraction complete | Spend
ProgressLine | Project office support | 1 | 2022-12-01 | 0.016667
ProgressLine | Project office support | 2 | 2023-02-01 | 0.033333
ProgressLine | Project office support | 3 | 2023-03-01 | 0.05
ProgressLine | Project office support | 4 | 2023-04-01 | 0.066667
ProgressLine | Project office support | 5 | 2023-05-01 | 0.083333
ProgressLine | Project office support | 6 | 2023-06-01 | 0.1
ProgressLine | Project office support | 7 | 2023-07-01 | 0.11667
ProgressLine | Project office support | 8 | 2023-08-01 | 0.13333
ProgressLine | Project office support | 9 | 2023-09-01 | 0.15
ProgressLine | Project office support | 10 | 2023-10-01 | 0.16667
ProgressLine | Project office support | 11 | 2023-11-01 | 0.18333
ProgressLine | Project office support | 12 | 2023-12-01 | 0.2
ProgressLine | Project office support | 13 | 2024-01-01 | 0.21667
ProgressLine | Project office support | 14 | 2024-02-01 | 0.23333
ProgressLine | Project office support | 15 | 2024-03-01 | 0.25
ProgressLine | Project office support | 16 | 2024-04-01 | 0.26667
ProgressLine | Project office support | 17 | 2024-05-01 | 0.28333
ProgressLine | Project office support | 18 | 2024-06-01 | 0.3
ProgressLine | Project office support | 19 | 2024-07-01 | 0.31667
ProgressLine | Project office support | 20 | 2024-08-01 | 0.33333
ProgressLine | Project office support | 21 | 2024-09-01 | 0.35
ProgressLine | Project office support | 22 | 2024-10-01 | 0.36667
ProgressLine | Project office support | 23 | 2024-11-01 | 0.38333
ProgressLine | Project office support | 24 | 2024-12-01 | 0.4
ProgressLine | Project office support | 25 | 2025-01-01 | 0.41667
ProgressLine | Project office support | 26 | 2025-02-01 | 0.43333
ProgressLine | Project office support | 27 | 2025-03-01 | 0.45
ProgressLine | Project office support | 28 | 2025-04-01 | 0.46667
ProgressLine | Project office support | 29 | 2025-05-01 | 0.48333
ProgressLine | Project office support | 30 | 2025-06-01 | 0.5
ProgressLine | Project office support | 31 | 2025-07-01 | 0.51667
ProgressLine | Project office support | 32 | 2025-08-01 | 0.53333
ProgressLine | Project office support | 33 | 2025-09-01 | 0.55
ProgressLine | Project office support | 34 | 2025-10-01 | 0.56667
ProgressLine | Project office support | 35 | 2025-11-01 | 0.58333
ProgressLine | Project office support | 36 | 2025-12-01 | 0.6
ProgressLine | Project office support | 37 | 2026-01-01 | 0.61667
ProgressLine | Project office support | 38 | 2026-02-01 | 0.63333
ProgressLine | Project office support | 39 | 2026-03-01 | 0.65
ProgressLine | Project office support | 40 | 2026-04-01 | 0.66667
ProgressLine | Project office support | 41 | 2026-05-01 | 0.68333
ProgressLine | Project office support | 42 | 2026-06-01 | 0.7
ProgressLine | Project office support | 43 | 2026-07-01 | 0.71667
ProgressLine | Project office support | 44 | 2026-08-01 | 0.73333
ProgressLine | Project office support | 45 | 2026-09-01 | 0.75
ProgressLine | Project office support | 46 | 2026-10-01 | 0.76667
ProgressLine | Project office support | 47 | 2026-11-01 | 0.78333
ProgressLine | Project office support | 48 | 2026-12-01 | 0.8
ProgressLine | Project office support | 49 | 2027-01-01 | 0.81667
ProgressLine | Project office support | 50 | 2027-02-01 | 0.83333
ProgressLine | Project office support | 51 | 2027-03-01 | 0.85
ProgressLine | Project office support | 52 | 2027-04-01 | 0.86667
ProgressLine | Project office support | 53 | 2027-05-01 | 0.88333
ProgressLine | Project office support | 54 | 2027-06-01 | 0.9
ProgressLine | Project office support | 55 | 2027-07-01 | 0.91667
ProgressLine | Project office support | 56 | 2027-08-01 | 0.93333
ProgressLine | Project office support | 57 | 2027-09-01 | 0.95
ProgressLine | Project office support | 58 | 2027-10-01 | 0.96667
ProgressLine | Project office support | 59 | 2027-11-01 | 0.98333
ProgressLine | Project office support | 60 | 2027-12-01 | 1
Update history
2022-06-21 | First version
Formulas:
Date = EDATE(D7,[LhARA Project Management])