## WP1-Prg
Date: | 2022-05-04 |  | Issue | 1
Project | LhARA | Laser-hybrid Accelerator for Radiobiological Applications
Work package | WP1 | LhARA Project Management
Manager | WPMs | Colin Whyte & Jason Parsons
Header | Task | Month | Date | Planned fraction complete | Planned value (£k) | Fraction complete | Spend (£k)
ProgressLine | Project office support | 1 | 2022-11-01 | 0.016667 | 14.5833 | 0.064372 | 56.3259
ProgressLine | Project office support | 2 | 2023-01-01 | 0.033333 | 29.1667 | 0.040642 | 35.562
ProgressLine | Project office support | 3 | 2023-02-01 | 0.05 | 43.75 | 0.076763 | 67.1672
ProgressLine | Project office support | 4 | 2023-03-01 | 0.066667 | 58.3333 | 0.09815 | 85.8814
ProgressLine | Project office support | 5 | 2023-04-01 | 0.083333 | 72.9167 | 0.06392 | 55.9299
ProgressLine | Project office support | 6 | 2023-05-01 | 0.1 | 87.5 | 0.070573 | 61.7515
ProgressLine | Project office support | 7 | 2023-06-01 | 0.11667 | 102.0833 | 0.15414 | 134.874
ProgressLine | Project office support | 8 | 2023-07-01 | 0.13333 | 116.6667 | 0.19657 | 171.9968
ProgressLine | Project office support | 9 | 2023-08-01 | 0.15 | 131.25 | 0.17256 | 150.9868
ProgressLine | Project office support | 10 | 2023-09-01 | 0.16667 | 145.8333 | 0.18383 | 160.8486
ProgressLine | Project office support | 11 | 2023-10-01 | 0.18333 | 160.4167 | 0.16728 | 146.371
ProgressLine | Project office support | 12 | 2023-11-01 | 0.2 | 175 | 0.12915 | 113.0019
ProgressLine | Project office support | 13 | 2023-12-01 | 0.21667 | 189.5833 | 0.20527 | 179.6142
ProgressLine | Project office support | 14 | 2024-01-01 | 0.23333 | 204.1667 | 0.30045 | 262.8929
ProgressLine | Project office support | 15 | 2024-02-01 | 0.25 | 218.75 | 0.30491 | 266.7971
ProgressLine | Project office support | 16 | 2024-03-01 | 0.26667 | 233.3333 | 0.24513 | 214.4919
ProgressLine | Project office support | 17 | 2024-04-01 | 0.28333 | 247.9167 | 0.24371 | 213.2494
ProgressLine | Project office support | 18 | 2024-05-01 | 0.3 | 262.5 | 0.2655 | 232.3156
ProgressLine | Project office support | 19 | 2024-06-01 | 0.31667 | 277.0833 | 0.30673 | 268.3845
ProgressLine | Project office support | 20 | 2024-07-01 | 0.33333 | 291.6667 | 0.31983 | 279.8474
ProgressLine | Project office support | 21 | 2024-08-01 | 0.35 | 306.25 | 0.37467 | 327.8326
ProgressLine | Project office support | 22 | 2024-09-01 | 0.36667 | 320.8333 | 0.35533 | 310.9096
ProgressLine | Project office support | 23 | 2024-10-01 | 0.38333 | 335.4167 | 0.38973 | 341.0114
ProgressLine | Project office support | 24 | 2024-11-01 | 0.4 | 350 | 0.39309 | 343.9562
ProgressLine | Project office support | 25 | 2024-12-01 | 0.41667 | 364.5833 | 0.41296 | 361.3357
ProgressLine | Project office support | 26 | 2025-01-01 | 0.43333 | 379.1667 | 0.4492 | 393.0539
ProgressLine | Project office support | 27 | 2025-02-01 | 0.45 | 393.75 | 0.45045 | 394.1422
ProgressLine | Project office support | 28 | 2025-03-01 | 0.46667 | 408.3333 | 0.50309 | 440.2071
ProgressLine | Project office support | 29 | 2025-04-01 | 0.48333 | 422.9167 | 0.49426 | 432.4788
ProgressLine | Project office support | 30 | 2025-05-01 | 0.5 | 437.5 | 0.50378 | 440.8039
ProgressLine | Project office support | 31 | 2025-06-01 | 0.51667 | 452.0833 | 0.53249 | 465.9317
ProgressLine | Project office support | 32 | 2025-07-01 | 0.53333 | 466.6667 | 0.5395 | 472.0619
ProgressLine | Project office support | 33 | 2025-08-01 | 0.55 | 481.25 | 0.59 | 516.2519
ProgressLine | Project office support | 34 | 2025-09-01 | 0.56667 | 495.8333
ProgressLine | Project office support | 35 | 2025-10-01 | 0.58333 | 510.4167
ProgressLine | Project office support | 36 | 2025-11-01 | 0.6 | 525
ProgressLine | Project office support | 37 | 2025-12-01 | 0.61667 | 539.5833
ProgressLine | Project office support | 38 | 2026-01-01 | 0.63333 | 554.1667
ProgressLine | Project office support | 39 | 2026-02-01 | 0.65 | 568.75
ProgressLine | Project office support | 40 | 2026-03-01 | 0.66667 | 583.3333
ProgressLine | Project office support | 41 | 2026-04-01 | 0.68333 | 597.9167
ProgressLine | Project office support | 42 | 2026-05-01 | 0.7 | 612.5
ProgressLine | Project office support | 43 | 2026-06-01 | 0.71667 | 627.0833
ProgressLine | Project office support | 44 | 2026-07-01 | 0.73333 | 641.6667
ProgressLine | Project office support | 45 | 2026-08-01 | 0.75 | 656.25
ProgressLine | Project office support | 46 | 2026-09-01 | 0.76667 | 670.8333
ProgressLine | Project office support | 47 | 2026-10-01 | 0.78333 | 685.4167
ProgressLine | Project office support | 48 | 2026-11-01 | 0.8 | 700
ProgressLine | Project office support | 49 | 2026-12-01 | 0.81667 | 714.5833
ProgressLine | Project office support | 50 | 2027-01-01 | 0.83333 | 729.1667
ProgressLine | Project office support | 51 | 2027-02-01 | 0.85 | 743.75
ProgressLine | Project office support | 52 | 2027-03-01 | 0.86667 | 758.3333
ProgressLine | Project office support | 53 | 2027-04-01 | 0.88333 | 772.9167
ProgressLine | Project office support | 54 | 2027-05-01 | 0.9 | 787.5
ProgressLine | Project office support | 55 | 2027-06-01 | 0.91667 | 802.0833
ProgressLine | Project office support | 56 | 2027-07-01 | 0.93333 | 816.6667
ProgressLine | Project office support | 57 | 2027-08-01 | 0.95 | 831.25
ProgressLine | Project office support | 58 | 2027-09-01 | 0.96667 | 845.8333
ProgressLine | Project office support | 59 | 2027-10-01 | 0.98333 | 860.4167
ProgressLine | Project office support | 60 | 2027-11-01 | 1 | 875
Update history
2022-06-21 | First version
Formulas:
Date = EDATE(D7,[LhARA Project Management])