## WP1-Prg
Date: | 2022-05-04 |  | Issue | 1
Project | LhARA | Laser-hybrid Accelerator for Radiobiological Applications
Work package | WP1 | LhARA Project Management
Manager | WPMs | Colin Whyte & Jason Parsons
Header | Task | Month | Date | Planned fraction complete | Planned value (£k) | Fraction complete | Spend (£k)
ProgressLine | Project office support | 1 | 2022-11-01 | 0.016667 | 14.5833 | 0.025733 | 22.5164
ProgressLine | Project office support | 2 | 2023-01-01 | 0.033333 | 29.1667 | 0.048229 | 42.2007
ProgressLine | Project office support | 3 | 2023-02-01 | 0.05 | 43.75 | 0.012303 | 10.7649
ProgressLine | Project office support | 4 | 2023-03-01 | 0.066667 | 58.3333 | 0.079237 | 69.332
ProgressLine | Project office support | 5 | 2023-04-01 | 0.083333 | 72.9167 | 0.0505 | 44.1877
ProgressLine | Project office support | 6 | 2023-05-01 | 0.1 | 87.5 | 0.12317 | 107.7708
ProgressLine | Project office support | 7 | 2023-06-01 | 0.11667 | 102.0833 | 0.09822 | 85.9427
ProgressLine | Project office support | 8 | 2023-07-01 | 0.13333 | 116.6667 | 0.15448 | 135.1664
ProgressLine | Project office support | 9 | 2023-08-01 | 0.15 | 131.25 | 0.15705 | 137.4187
ProgressLine | Project office support | 10 | 2023-09-01 | 0.16667 | 145.8333 | 0.18705 | 163.6694
ProgressLine | Project office support | 11 | 2023-10-01 | 0.18333 | 160.4167 | 0.2113 | 184.8897
ProgressLine | Project office support | 12 | 2023-11-01 | 0.2 | 175 | 0.18441 | 161.3558
ProgressLine | Project office support | 13 | 2023-12-01 | 0.21667 | 189.5833 | 0.23111 | 202.2179
ProgressLine | Project office support | 14 | 2024-01-01 | 0.23333 | 204.1667 | 0.2476 | 216.6481
ProgressLine | Project office support | 15 | 2024-02-01 | 0.25 | 218.75 | 0.29166 | 255.1998
ProgressLine | Project office support | 16 | 2024-03-01 | 0.26667 | 233.3333 | 0.26188 | 229.1492
ProgressLine | Project office support | 17 | 2024-04-01 | 0.28333 | 247.9167 | 0.30523 | 267.0778
ProgressLine | Project office support | 18 | 2024-05-01 | 0.3 | 262.5 | 0.33654 | 294.4739
ProgressLine | Project office support | 19 | 2024-06-01 | 0.31667 | 277.0833 | 0.41879 | 366.4436
ProgressLine | Project office support | 20 | 2024-07-01 | 0.33333 | 291.6667 | 0.34178 | 299.0611
ProgressLine | Project office support | 21 | 2024-08-01 | 0.35 | 306.25 | 0.41029 | 359.0028
ProgressLine | Project office support | 22 | 2024-09-01 | 0.36667 | 320.8333 | 0.3525 | 308.4369
ProgressLine | Project office support | 23 | 2024-10-01 | 0.38333 | 335.4167 | 0.39057 | 341.7487
ProgressLine | Project office support | 24 | 2024-11-01 | 0.4 | 350 | 0.38102 | 333.39
ProgressLine | Project office support | 25 | 2024-12-01 | 0.41667 | 364.5833 | 0.39178 | 342.8115
ProgressLine | Project office support | 26 | 2025-01-01 | 0.43333 | 379.1667 | 0.44308 | 387.6961
ProgressLine | Project office support | 27 | 2025-02-01 | 0.45 | 393.75 | 0.44293 | 387.5641
ProgressLine | Project office support | 28 | 2025-03-01 | 0.46667 | 408.3333 | 0.42055 | 367.983
ProgressLine | Project office support | 29 | 2025-04-01 | 0.48333 | 422.9167 | 0.42889 | 375.2758
ProgressLine | Project office support | 30 | 2025-05-01 | 0.5 | 437.5 | 0.53989 | 472.4077
ProgressLine | Project office support | 31 | 2025-06-01 | 0.51667 | 452.0833 | 0.51701 | 452.386
ProgressLine | Project office support | 32 | 2025-07-01 | 0.53333 | 466.6667 | 0.5211 | 455.9645
ProgressLine | Project office support | 33 | 2025-08-01 | 0.55 | 481.25 | 0.58235 | 509.5551
ProgressLine | Project office support | 34 | 2025-09-01 | 0.56667 | 495.8333 | 0.61637 | 539.3263
ProgressLine | Project office support | 35 | 2025-10-01 | 0.58333 | 510.4167 | 0.65756 | 575.3655
ProgressLine | Project office support | 36 | 2025-11-01 | 0.6 | 525 | 0.52754 | 461.599
ProgressLine | Project office support | 37 | 2025-12-01 | 0.61667 | 539.5833 | 0.62081 | 543.2059
ProgressLine | Project office support | 38 | 2026-01-01 | 0.63333 | 554.1667 | 0.59521 | 520.8066
ProgressLine | Project office support | 39 | 2026-02-01 | 0.65 | 568.75 | 0.69576 | 608.787
ProgressLine | Project office support | 40 | 2026-03-01 | 0.66667 | 583.3333 | 0.68021 | 595.1854
ProgressLine | Project office support | 41 | 2026-04-01 | 0.68333 | 597.9167 | 0.72524 | 634.5836
ProgressLine | Project office support | 42 | 2026-05-01 | 0.7 | 612.5 | 0.70835 | 619.8048
ProgressLine | Project office support | 43 | 2026-06-01 | 0.71667 | 627.0833 | 0.68612 | 600.3577
ProgressLine | Project office support | 44 | 2026-07-01 | 0.73333 | 641.6667 | 0.73866 | 646.3239
ProgressLine | Project office support | 45 | 2026-08-01 | 0.75 | 656.25 | 0.73498 | 643.1113
ProgressLine | Project office support | 46 | 2026-09-01 | 0.76667 | 670.8333 | 0.80239 | 702.094
ProgressLine | Project office support | 47 | 2026-10-01 | 0.78333 | 685.4167 | 0.77131 | 674.8938
ProgressLine | Project office support | 48 | 2026-11-01 | 0.8 | 700 | 0.71234 | 623.2995
ProgressLine | Project office support | 49 | 2026-12-01 | 0.81667 | 714.5833 | 0.79107 | 692.1882
ProgressLine | Project office support | 50 | 2027-01-01 | 0.83333 | 729.1667 | 0.81628 | 714.2423
ProgressLine | Project office support | 51 | 2027-02-01 | 0.85 | 743.75 | 0.88723 | 776.3238
ProgressLine | Project office support | 52 | 2027-03-01 | 0.86667 | 758.3333 | 0.85993 | 752.4411
ProgressLine | Project office support | 53 | 2027-04-01 | 0.88333 | 772.9167 | 0.92301 | 807.6376
ProgressLine | Project office support | 54 | 2027-05-01 | 0.9 | 787.5 | 0.91889 | 804.0318
ProgressLine | Project office support | 55 | 2027-06-01 | 0.91667 | 802.0833 | 0.88723 | 776.3276
ProgressLine | Project office support | 56 | 2027-07-01 | 0.93333 | 816.6667 | 0.93649 | 819.4314
ProgressLine | Project office support | 57 | 2027-08-01 | 0.95 | 831.25 | 0.91948 | 804.5425
ProgressLine | Project office support | 58 | 2027-09-01 | 0.96667 | 845.8333 | 0.94264 | 824.812
ProgressLine | Project office support | 59 | 2027-10-01 | 0.98333 | 860.4167 | 0.94539 | 827.219
ProgressLine | Project office support | 60 | 2027-11-01 | 1 | 875 | 0.99439 | 870.0901
Update history
2022-06-21 | First version
Formulas:
Date = EDATE(D7,[LhARA Project Management])