## WP1-Prg
Date: | 2022-05-04 |  | Issue | 1
Project | LhARA | Laser-hybrid Accelerator for Radiobiological Applications
Work package | WP1 | LhARA Project Management
Manager | WPMs | Colin Whyte & Jason Parsons
Header | Task | Month | Date | Planned fraction complete | Planned value (£k) | Fraction complete | Spend (£k)
ProgressLine | Project office support | 1 | 2022-11-01 | 0.041667 | 7.0833 | 0.044874 | 7.6286
ProgressLine | Project office support | 2 | 2022-12-01 | 0.083333 | 14.1667 | 0.09511 | 16.1687
ProgressLine | Project office support | 3 | 2023-01-01 | 0.125 | 21.25 | 0.10972 | 18.6521
ProgressLine | Project office support | 4 | 2023-02-01 | 0.16667 | 28.3333 | 0.16871 | 28.6809
ProgressLine | Project office support | 5 | 2023-03-01 | 0.20833 | 35.4167 | 0.16887 | 28.7081
ProgressLine | Project office support | 6 | 2023-04-01 | 0.25 | 42.5 | 0.231 | 39.27
ProgressLine | Project office support | 7 | 2023-05-01 | 0.29167 | 49.5833 | 0.30208 | 51.3542
ProgressLine | Project office support | 8 | 2023-06-01 | 0.33333 | 56.6667 | 0.33564 | 57.0593
ProgressLine | Project office support | 9 | 2023-07-01 | 0.375 | 63.75 | 0.39943 | 67.9038
ProgressLine | Project office support | 10 | 2023-08-01 | 0.41667 | 70.8333 | 0.42186 | 71.7165
ProgressLine | Project office support | 11 | 2023-09-01 | 0.45833 | 77.9167 | 0.42407 | 72.0911
ProgressLine | Project office support | 12 | 2023-10-01 | 0.5 | 85 | 0.50446 | 85.7589
ProgressLine | Project office support | 13 | 2023-11-01 | 0.54167 | 92.0833 | 0.56344 | 95.7854
ProgressLine | Project office support | 14 | 2023-12-01 | 0.58333 | 99.1667 | 0.57821 | 98.295
ProgressLine | Project office support | 15 | 2024-01-01 | 0.625 | 106.25 | 0.62855 | 106.8536
ProgressLine | Project office support | 16 | 2024-02-01 | 0.66667 | 113.3333 | 0.67711 | 115.1084
ProgressLine | Project office support | 17 | 2024-03-01 | 0.70833 | 120.4167 | 0.72856 | 123.8558
ProgressLine | Project office support | 18 | 2024-04-01 | 0.75 | 127.5 | 0.76239 | 129.607
ProgressLine | Project office support | 19 | 2024-05-01 | 0.79167 | 134.5833 | 0.77295 | 131.4019
ProgressLine | Project office support | 20 | 2024-06-01 | 0.83333 | 141.6667 | 0.83054 | 141.191
ProgressLine | Project office support | 21 | 2024-07-01 | 0.875 | 148.75 | 0.88812 | 150.9804
ProgressLine | Project office support | 22 | 2024-08-01 | 0.91667 | 155.8333 | 0.90175 | 153.2967
ProgressLine | Project office support | 23 | 2024-09-01 | 0.95833 | 162.9167 | 0.9617 | 163.489
ProgressLine | Project office support | 24 | 2024-10-01 | 1 | 170 | 0.9565 | 162.6043
Update history
2022-06-21 | First version
Formulas:
Date = EDATE(D7,[LhARA Project Management]-1)